## Sheet1
Ref ID | Risk Title | Description | Risk Category | Date Identified | Probability Of Ocurrence VERY LOW (1) to VERY HIGH (5) | Damage/Impact level VERY LOW (1) to VERY HIGH (5) | Risk Factor = (probability of occurrence) x (damage) AUTOMATIC CALCULATION | Mitigation Strategy | Person in Charge | Status | Date closed
R01 | Team Skill Gap | Skill gap in full-stack development due to new team member (Klaudia) has limited coding experience in backend and database technologies. | Team | 17/03/2026 | 4 | 4 | 16 | Assign small, well‑defined tasks (frontend styling and administrative tasks) to new member. Daniel and Petra to handle complex backend and frontend logic. Utilize online resources (tutorials/documentation). | Petra | Closed | 2026-12-05
R02 | Inadequate Time/Cost Estimate | Project time and effort may be underestimated after team restructuring. Original project estimates assumed three developers; with two developers and a skill gap, deadlines and scope are unrealistic. | Planning | 17/03/2026 | 3 | 4 | 12 | Re-estimate the remaining work with the new team of two developers (Daniel and Petra). Focus on delivering a functional core before adding "nice-to-have" features. | Petra | Closed | 2026-03-04
R03 | Technical Complexity | Interating multiple technologies (MongoDB, Elasticsearch, Socket.IO) poses integration and performance risks. | Complexity | 17/03/2026 | 3 | 4 | 12 | Create a clear Integration plan and API documentation. Focus on core tech first. Develop and test integrations in isolation before merging. | Daniel | Closed | 13/04/2026
R04 | Ineffective Communication | Ineffective communication after team change. | Planning | 17/03/2026 | 3 | 3 | 9 | Use YouTrack to assign tasks and track progress. Ensure all documentation (roadmap, API specs) is updated to reflect the new team structure and responsibilities. | Petra | Closed | 28/04/2026
R05 | Low User Adoption | Students may not use or trust the platform | Users | 17/03/2026 | 3 | 3 | 9 | Focus on usability, clean UI/UX, gather early feedback from peers. | Petra & Klaudia | Closed | 23/04/2026
R06 | Hardware Constraint Risk | System performance failures on legacy desktop hardware due to high frontend weight. | Functionality | 17/03/2026 | 3 | 3 | 9 | Optimize frontend assets (code splitting, lazy loading). Test on low‑end devices during development. Use lightweight UI components. | Petra | Closed | 15/04/2026
R07 | Data Integrity/Staleness | External scholarship data from APIs or scrapers may become outdated, leading to student frustration. | Quality | 17/03/2026 | 3 | 3 | 9 | Implement regular data refresh jobs. Display timestamps for last update. Consider manual verification for critical data. | Daniel | Closed | 2026-06-04
R08 | API Breaking Changes | CareerOneStop or other external providers change their JSON structure, breaking Application Tier logic. | Functionality | 17/03/2026 | 2 | 4 | 8 | Build an abstraction layer for external API calls. Use schema validation and versioning. Monitor API changelogs. | Daniel | Closed | 2026-10-04
R09 | Unauthorized Data Access | Insecure handling of JWT tokens or API keys, exposing student account data. | Functionality | 17/03/2026 | 2 | 5 | 10 | Store secrets in environment variables. Use HTTPS, short‑lived tokens, and proper authentication flows. Conduct a security review before launch. | Daniel | Closed | 2026-07-04
R10 | Language/Accessibility Barrier | Complex academic English in scholarship descriptions may alienate non-native speakers. | Users | 17/03/2026 | 3 | 3 | 9 | Provide simplified summaries or translations. Use clear, plain language in UI. Consider offering a glossary of common terms.